## BRD
Application | No. | Obstacle | Type | Proposed solution | Initiation Date | Estimated completion date | Completion date | Current status | Assigned to | Result
Sys Admin | 1 | We need to prevent unauthorized users fom accessing to specific data | New feature | create custom responsibilities with a specific data group | 25/2/2025 | 26/2/2025 | 26/2/2025 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 2 | Manual data entry in spreadsheets leads to errors. | New feature | Automated data capture and validation in Oracle EBS. | 2025-02-27 | 2025-02-27 | 2025-02-27 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 3 | Lack of real-time inventory visibility. | New feature | Real-time inventory tracking and reporting. | 2025-02-28 | 2025-02-28 | 2025-02-28 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 4 | Difficulty in tracking inventory across branches. | New feature | Centralized inventory management with multiple organizations and subinventories. | 2025-03-01 | 2025-03-01 | 2025-03-01 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 5 | Clasify Inventory between sellable, stocable and defective items | upgrade | Define item status (Active or Inactive) | 2025-03-02 | 2025-03-02 | 2025-03-02 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 6 | No standardized item master data. | New feature | Centralized item master with defined attributes and categories. | 2025-03-03 | 2025-03-03 | 2025-03-03 | Closed | Mohamed Ahmed | Completed
Oracle Inventory (INV) | 7 | ununified costing Methods | New feature | unified average costing method | 2025-03-04 | 2025-03-04 | 2025-03-04 | Closed | Mohamed Ahmed | Completed
Oracle Inventory (INV) | 8 | inaccurate physical inventory onhad. | New feature | contolled physical inventory processes. | 2025-03-05 | 2025-03-05 | 2025-03-05 | Closed | Mohamed Ahmed | Completed
Oracle Inventory (INV) | 9 | undefined measurement units | New feature | defined UOM definitions and conversions. | 2025-03-06 | 2025-03-06 | 2025-03-06 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 10 | sudden inventory shortage and overstocking for some items | upgrade | Apply Min max Planning with org source ALX | 2025-03-06 | 2025-03-06 | 2025-03-06 | Closed | Mohamed Ahmed | Completed
Oracle Inventory (INV) | 11 | Unaccepted move orders still on hold too much time | upgrade | adjust move order timeout to be 3 days only in org parameters | 2025-03-06 | 2025-03-06 | 2025-03-06 | Closed | Mohamed Ahmed | Completed
Oracle Inventory (INV) | 12 | Lack of historical data for demand forecasting. | New feature | Historical data analysis for demand forecasting and planning. | 2025-03-06 | 2025-03-06 | 2025-03-06 | Closed | Mostafa Noseur | Completed
Oracle Inventory (INV) | 13 | No rules to regulate inventory transactions | New feature | create matrials status to control items transactions | 2025-03-07 | 2025-03-07 | 2025-03-07 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 14 | october org and new cairo org must not be able to check onhand quantities | New feature | Create 3 custome responsibilites | 2025-03-07 | 2025-03-07 | 2025-03-07 | Closed | Mostafa Noseur | Completed
Oracle Inventory (INV) | 15 | negative balance is not accepted | New feature | disable allow negative balance button | 2025-03-08 | 2025-03-08 | 2025-03-08 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 16 | Manual tracking of inter-Org transfers leads to delays, data inaccuracies, and lack of real-time visibility | upgrade | apply intransit shipment type and standard Reciept routing | 2025-03-08 | 2025-03-08 | 2025-03-08 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 17 | defective units being issued to employees | New feature | Create lot control for spare parts items and material status | 2025-03-09 | 2025-03-09 | 2025-03-09 | Closed | Doaa torkey | Completed
Oracle Inventory (INV) | 18 | Establish Item behaviours and enable bulk item creation | upgrade | Create Item Templates | 1899-12-31 | 1899-12-31 | 1899-12-31 | Closed | Mostafa Noseur | Completed
Oracle Purchasing (PO) | 18 | No integration between inventory and purchasing. | New feature | Seamless integration between Inventory and Purchasing modules.
Oracle Purchasing (PO) | 19 | Manual creation and tracking of purchase orders. | New feature | Automated purchase order creation and tracking.
Oracle Purchasing (PO) | 20 | Lack of supplier performance tracking. | New feature | Supplier performance monitoring and reporting.
Oracle Purchasing (PO) | 21 | Manual approval processes for purchase orders. | New feature | Automated approval workflows for purchase orders.
Oracle Order Management (OM) | 22 | No integration between inventory and sales. | New feature | Integration between Inventory and Order Management for accurate order fulfillment.
Oracle Order Management (OM) | 23 | Manual creation and tracking of sales orders. | New feature | Automated sales order creation and tracking.
Oracle Order Management (OM) | 24 | Difficulty in managing pricing and discounts. | New feature | Centralized pricing and discount management.
Oracle Order Management (OM) | 25 | No visibility into order status (e.g., pending, shipped). | New feature | Real-time order status tracking.
Oracle Cost Management (CST) | 26 | No standardized costing methods. | New feature | Standardized costing methods (e.g., standard costing, average costing).
Oracle Cost Management (CST) | 27 | Manual calculation of inventory valuation. | New feature | Automated inventory valuation and cost tracking.
Formulas:
Estimated completion date = [Initiation Date]
Completion date = [Estimated completion date]
Initiation Date = [Initiation Date, row above]+1